## 修复记录Nov12
工程师
月份 | 2020-11-01 | 周 | 2020-11-12
| QA | QA | QA | QA |  | QA | QA | 开发管理 | 工程师 | 自动计算 | QA | 工程师 | 工程师 | 工程师 | 工程师 | 工程师
序号 | 产品 | 分类 | Ticket no. | Link | 工程师 | 严重程度 | 紧急程度 | 计划工作时长（天） | 开始时间 | 目标完成时间 | 实际完成时间 | 当前状态 | 原代码截图 | 问题原因 | 解决方案 | 其他功能影响评估（数据流，其他功能影响评估）
1 | Admin | Bug | #140 | https://github.com/bridge5/amss-api-issues/issues/140 | Bill | QA: 5; QA: 5
2 | Admin | Bug | #118 | https://github.com/bridge5/amss-api-issues/issues/118 | Bill | QA: 5; QA: 5
3 | Account | Bug | #139 | https://github.com/bridge5/amss-api-issues/issues/139 | Bill | QA: 1; QA: 3
4 | Admin | Bug | #112 | https://github.com/bridge5/amss-api-issues/issues/112 | Bill | QA: 5; QA: 2; QA: 2020-11-12
5 | Admin | Bug | #46 | https://github.com/bridge5/amss-api-issues/issues/46 | Heri | QA: 5; QA: 2
6 | UI | Bug |  | https://github.com/bridge5/amss-workbench/issues/3372 https://github.com/bridge5/amss-workbench/issues/3436 https://github.com/bridge5/amss-workbench/issues/3363 | Bill | QA: 3; QA: 2
7 | Retail1 | Bug | #45 | https://github.com/bridge5/amss-api-issues/issues/45 | Fenghe | QA: 5; QA: 5
8 | Office1 | Bug | #102 | https://github.com/bridge5/amss-api-issues/issues/102 | Fenghe | QA: 5; QA: 5; QA: 2020-11-12
9 | Office1 | Bug | #249 | https://github.com/bridge5/amss-api-issues/issues/249 | Fenghe | QA: 5; QA: 5
10 | Hotel1 | Bug | #273 | https://github.com/bridge5/amss-api-issues/issues/273 | Fenghe | QA: 5; QA: 5; QA: 2020-11-12
11 | Sales1 | Bug | #111 | https://github.com/bridge5/amss-api-issues/issues/111 | Fenghe | QA: 4; QA: 5; QA: 2020-11-12
12 | Sales1 | Bug | #276 | https://github.com/bridge5/amss-api-issues/issues/276 | Fenghe | QA: 3; QA: 5
13 | Office1 | Feature | #284 | https://github.com/bridge5/amss-api-issues/issues/284 | Fenghe | QA: 5; QA: 2
14 | Sales1 | Bug | #87 | https://github.com/bridge5/amss-api-issues/issues/87 | Heri | QA: 4; QA: 4; QA: 2020-11-12
15 | Sales2 | Bug | #70 | https://github.com/bridge5/amss-api-issues/issues/70 | Heri | QA: 4; QA: 2
16 | Sales1 | Bug | #319 | https://github.com/bridge5/amss-api-issues/issues/319 | Heri | QA: 2; QA: 4; QA: 2020-11-12
17 | UI | Bug | #1720 | https://github.com/bridge5/amss-workbench/issues/1720 | Jonny | QA: 4; QA: 3
18 |  | Feature | #3342 | https://github.com/bridge5/amss-workbench/issues/3342 | Jonny | QA: 1; QA: 3; QA: Cancelled
19 | UI | Bug | #1882 | https://github.com/bridge5/amss-workbench/issues/1882 | Jonny | QA: 1; QA: 3; QA: 2020-11-12
20 | UI | Bug | #1889 | https://github.com/bridge5/amss-workbench/issues/1889 | Jonny | QA: 1; QA: 3; QA: 2020-11-12
21 | UI | Feature | #3658 | https://github.com/bridge5/amss-workbench/issues/3658 | Liaoxuan | QA: 1; QA: 3
22 | UI | Bug | #943 | https://github.com/bridge5/amss-workbench/issues/943 | Liulv | QA: 2; QA: 4; QA: 2020-11-12
23 | UI | Feature | #901 | https://github.com/bridge5/amss-workbench/issues/901 | Liulv | QA: 1; QA: 1; QA: 2020-11-12
24 | Valuation | Bug | #283 | https://github.com/bridge5/amss-api-issues/issues/283 | Yujie | QA: 4; QA: 2; QA: 2020-11-12
25 | Office1 | Feature | #280 | https://github.com/bridge5/amss-api-issues/issues/280 | yujie | QA: 1; QA: 1; QA: 2020-11-12
26 | Office1 | Feature | #281 | https://github.com/bridge5/amss-api-issues/issues/281 | yujie | QA: 1; QA: 1; QA: 2020-11-12
27 | Office1 | Bug | #320 | https://github.com/bridge5/amss-api-issues/issues/320 | yujie | QA: 1; QA: 5; QA: 2020-11-12
28 | UI | Feature | #4031 | https://github.com/bridge5/amss-workbench/issues/4031 | Zhufu | QA: 4; QA: 5; QA: 2020-11-12
29 | UI | Feature | #4032 | https://github.com/bridge5/amss-workbench/issues/4032 | Zhufu | QA: 4; QA: 5; QA: 2020-11-12
30 | UI | Bug | #1237 | https://github.com/bridge5/amss-workbench/issues/1237 | Zhufu | QA: 3; QA: 5; QA: 2020-11-12
31 | UI | Bug | #4127 | https://github.com/bridge5/amss-workbench/issues/4127 | Zhufu | QA: 1; QA: 5; QA: 2020-11-12
32 | UI | Bug | #4133 | https://github.com/bridge5/amss-workbench/issues/4133 | zhufu | QA: 2; QA: 2; QA: 2020-11-12

## 修复记录Nov19
工程师
月份 | 2020-11-01 | 周 | 2020-11-19
| QA | QA | QA | QA |  | QA | QA | 开发管理 | 工程师 | 自动计算 | QA | 工程师 | 工程师 | 工程师 | 工程师 | 工程师
序号 | 产品 | 分类 | Ticket no. | Link | 工程师 | 严重程度 | 紧急程度 | 计划工作时长（天） | 开始时间 | 目标完成时间 | 实际完成时间 | 当前状态 | 原代码截图 | 问题原因 | 解决方案 | 其他功能影响评估（数据流，其他功能影响评估）
1 | Sales1 | Feature | #900 | https://github.com/bridge5/amss-workbench/issues/900 | Bill | QA: 2; QA: 1
2 | Sales1 | Feature | #1311 | https://github.com/bridge5/amss-workbench/issues/1311 | Bill | QA: 2; QA: 2
3 | Sales1 | Feature | #2568 | https://github.com/bridge5/amss-workbench/issues/2568 | Bill | bar: QA to QA
4 | Sales1 | Feature | #1987 | https://github.com/bridge5/amss-workbench/issues/1987 | Bill | QA: 3; QA: 5
5 | Sales1 | Feature | #1900 | https://github.com/bridge5/amss-workbench/issues/1900 | Bill | QA: 1; QA: 3
6 | Sales2 | Bug | #3405 | https://github.com/bridge5/amss-workbench/issues/3405 | Bill | QA: 1; QA: 2
7 | Sales1 | Feature | #2589 | https://github.com/bridge5/amss-workbench/issues/2589 | Bill | QA: 5; QA: 1; 开发管理: need bill and liulv
8 | Office1 | Bug | #2248 | https://github.com/bridge5/amss-workbench/issues/2248 | Bill | QA: 3; QA: 2
9 | Retail1 | Bug | #543 | https://github.com/bridge5/amss-workbench/issues/543 | Bill | QA: 1; QA: 1; QA: 2020-11-19
10 | Sales1 | Feature | #317 | https://github.com/bridge5/amss-api-issues/issues/317 | Fenghe & Heri | [11 empty] | This one need 2 developer
11 | UI | Bug | #4139 | https://github.com/bridge5/amss-workbench/issues/4139 | Liaoxuan | QA: 1; QA: 4; QA: 2020-11-19
12 | UI | Bug | #4165 | https://github.com/bridge5/amss-workbench/issues/4165 | Liaoxuan | QA: 5; QA: 4; QA: 2020-11-19
13 | 康养1 | Bug | #4182 | https://github.com/bridge5/amss-workbench/issues/4182 | Liaoxuan | QA: 1; QA: 4; QA: 2020-11-19
14 | 康养1 | Feature | #4181 | https://github.com/bridge5/amss-workbench/issues/4181 | Liaoxuan | QA: 1; QA: 4; QA: 2020-11-19
15 | 康养1 | Bug | #4172 | https://github.com/bridge5/amss-workbench/issues/4172 | Liaoxuan | QA: 1; QA: 4
16 | 康养1 | Bug | #4168 | https://github.com/bridge5/amss-api-issues/issues/342 | Yingcheng | QA: 1; QA: 4; QA: 2020-11-19
17 | 康养1 | Bug | #4107 | https://github.com/bridge5/amss-workbench/issues/4107 | Liaoxuan | QA: 1; QA: 3
18 | 康养1 | Bug | #4132 | https://github.com/bridge5/amss-workbench/issues/4132 | Liaoxuan | QA: 1; QA: 4; QA: 2020-11-19
19 | Sales1 | Bug | #1548 | https://github.com/bridge5/amss-api-issues/issues/345 | Heri | QA: 1; QA: 2
20 | Sales1 | Feature | #2589 | https://github.com/bridge5/amss-workbench/issues/2589 | Liulv | QA: 5; QA: 1 | This issue need 2 dev fix
21 | 康养1 | Bug | #4178 | https://github.com/bridge5/amss-workbench/issues/4178 | Liaoxuan | QA: 1; QA: 5
22 | 康养1 | Bug | #4169 | https://github.com/bridge5/amss-workbench/issues/4169 | Liaoxuan | QA: 3; QA: 5
23 | 康养1 | Feature | #4174 | https://github.com/bridge5/amss-workbench/issues/4174 | Liaoxuan | QA: 2; QA: 5
24 | 康养1 | Bug | #4173 | https://github.com/bridge5/amss-workbench/issues/4173 | Liaoxuan | QA: 4; QA: 4
25 | 康养1 | Bug | #4167 | https://github.com/bridge5/amss-workbench/issues/4167 | Liaoxuan | QA: 1; QA: 3
26 | 康养1 | Bug | #4160 | https://github.com/bridge5/amss-workbench/issues/4160 | Liaoxuan | bar: QA to QA
27 | 康养1 | Bug | #4159 | https://github.com/bridge5/amss-workbench/issues/4159 | Liaoxuan | QA: 1; QA: 3
28 | 康养1 | Bug | #4158 | https://github.com/bridge5/amss-workbench/issues/4158 | Liaoxuan | QA: 1; QA: 3
29 | 康养1 | Bug | #4156 | https://github.com/bridge5/amss-workbench/issues/4156 | Liaoxuan | bar: QA to QA
30 | 康养1 | Bug | #4155 | https://github.com/bridge5/amss-workbench/issues/4155 | Liaoxuan | QA: 3; QA: 5
31 | 康养1 | Bug | #4154 | https://github.com/bridge5/amss-workbench/issues/4154 | Liaoxuan | bar: QA to QA
32 | 康养1 | Bug | #4161 | https://github.com/bridge5/amss-workbench/issues/4161 | Liaoxuan | bar: QA to QA
33 | 康养1 | Feature | #4179 | https://github.com/bridge5/amss-workbench/issues/4179 | Liaoxuan | QA: 3; QA: 3
34 | 康养1 | Bug | #4157 | https://github.com/bridge5/amss-workbench/issues/4157 | Liaoxuan | bar: QA to QA
35 | Office1 | Bug | #305 | https://github.com/bridge5/amss-api-issues/issues/305 | Yujie | QA: 2; QA: 4; QA: 2020-11-19
36 | Office1 | Bug | #327 | https://github.com/bridge5/amss-api-issues/issues/327 | Yujie | QA: 1; QA: 2; QA: 2020-11-19
37 | Sales1 | Bug | #4051 | https://github.com/bridge5/amss-workbench/issues/4051 | Zhufu | QA: 1; QA: 5; QA: 2020-11-19
38 | Mixeduse | Feature | #4093 | https://github.com/bridge5/amss-workbench/issues/4093 | Zhufu | QA: 3; QA: 3; QA: 2020-11-19
39 | Sales1 | Bug | #317 | https://github.com/bridge5/amss-api-issues/issues/317 | Heri and Fenghe | QA: 4; QA: 2 | This one need 2 dev
40 | Sales1 and Sales 2 |  | #339 | https://github.com/bridge5/amss-api-issues/issues/339 | Heri | QA: 4; QA: 5; QA: 2020-11-19
41 | Hotel | Bug | #301 | https://github.com/bridge5/amss-api-issues/issues/301 | Shifeng | QA: 1; QA: 5; QA: 2020-11-19
42 | 康养 | Bug | #326 | https://github.com/bridge5/amss-api-issues/issues/326 | Shifeng | QA: 1; QA: 3
43 | 康养 | Bug | #318 | https://github.com/bridge5/amss-workbench/issues/4198 | Liaoxuan | QA: 1; QA: 3
44 | 康养 | Bug | #143 | https://github.com/bridge5/amss-api-issues/issues/143 | Yingcheng | QA: 1; QA: 3
45 | Hotel1 | Bug | #3658 | https://github.com/bridge5/amss-workbench/issues/3658 | Liaoxuan | QA: 1; QA: 3
46 | Hotel1 | Bug | #256 | https://github.com/bridge5/amss-api-issues/issues/256 | Shifeng | QA: 1; QA: 5
47 | 康养 | Bug | #354 | https://github.com/bridge5/amss-api-issues/issues/354 | xiaozhou | QA: 1; QA: 4; QA: 2020-11-19
48 | 康养 | Bug | #356 | https://github.com/bridge5/amss-api-issues/issues/356 | Yujie | QA: 4; QA: 5
49 | 康养 | Bug | #357 | https://github.com/bridge5/amss-api-issues/issues/357 | xiaozhou | QA: 3; QA: 4
50 | 康养 | Feature | #359 | https://github.com/bridge5/amss-api-issues/issues/359 | Yingcheng | QA: 1; QA: 3
51 | 康养 | Bug | #361 | https://github.com/bridge5/amss-api-issues/issues/361 | Fenghe | QA: 3; QA: 5
52 | 康养 | Bug | #362 | https://github.com/bridge5/amss-api-issues/issues/362 | Yingcheng | QA: 2; QA: 4; QA: 2020-11-19
53 | 康养 | Bug | #363 | https://github.com/bridge5/amss-api-issues/issues/363 | Shifeng | QA: 2; QA: 5; QA: 2020-11-19
54 | Sales 1and Sales 2 | Feature | #307 | https://github.com/bridge5/amss-api-issues/issues/307 | Heri | QA: 1; QA: 4; QA: QA Testing
55 | 康养 | Bug | #4214 | https://github.com/bridge5/amss-workbench/issues/4214 | Liaoxuan | QA: 1; QA: 5
56 | 康养 | Bug | #4215 | https://github.com/bridge5/amss-workbench/issues/4215 | Liaoxuan | QA: 2; QA: 4
57 | 康养 | Bug | #4218 | https://github.com/bridge5/amss-workbench/issues/4218 | Liaoxuan | QA: 3; QA: 4
58 | 康养 | Feature | #4224 | https://github.com/bridge5/amss-workbench/issues/4224 | Liaoxuan | QA: 1; QA: 5
59 | 康养 | Bug | #4225 | https://github.com/bridge5/amss-workbench/issues/4225 | Liaoxuan | QA: 1; QA: 4
60 | 康养 | Bug | #335 | https://github.com/bridge5/amss-api-issues/issues/335 | Fenghe | QA: 1; QA: 4

## 修复记录Nov27
工程师
月份 | 2020-11-01 | 周 | 2020-11-27
| QA | QA | QA | QA |  | QA | QA | 开发管理 | 工程师 | 自动计算 | QA | 工程师 | 工程师 | 工程师 | 工程师 | 工程师
序号 | 产品 | 分类 | Ticket no. | Link | 工程师 | 严重程度 | 紧急程度 | 计划工作时长（天） | 开始时间 | 目标完成时间 | 实际完成时间 | 当前状态 | 原代码截图 | 问题原因 | 解决方案 | 其他功能影响评估（数据流，其他功能影响评估）
1 | Mixeduse 1 | Bug | #3363 | https://github.com/bridge5/amss-workbench/issues/3363 | Zhufu | QA: 2; QA: 3
2 | Sales 1 | Feature | #3722 | https://github.com/bridge5/amss-workbench/issues/3722 | Heri and Bill | QA: 3; QA: 2; 开发管理: need bill and heri
3 | Mixeduse 1 | Bug | #4206 | https://github.com/bridge5/amss-workbench/issues/4206 | Zhufu | QA: 1; QA: 2
4 | Office 1 | Bug | #4212 | https://github.com/bridge5/amss-workbench/issues/4212 | Jonny | QA: 3; QA: 3
5 | 康养1 | Bug | #4107 | https://github.com/bridge5/amss-workbench/issues/4107 | Liaoxuan | QA: 1; QA: 3
6 | 康养1 | Bug | #4208 | https://github.com/bridge5/amss-workbench/issues/4208 | Liaoxuan | QA: 1; QA: 3
7 | 康养1 | Bug | #4210 | https://github.com/bridge5/amss-workbench/issues/4210 | Liaoxuan | QA: 1; QA: 3
8 | 康养1 | Bug | #4215 | https://github.com/bridge5/amss-workbench/issues/4215 | Liaoxuan | QA: 2; QA: 4
9 | 康养1 | Bug | #4218 | https://github.com/bridge5/amss-workbench/issues/4218 | Liaoxuan | QA: 3; QA: 4
10 | 康养1 | Feature | #4224 | https://github.com/bridge5/amss-workbench/issues/4224 | Liaoxuan | QA: 1; QA: 5
11 | 康养1 | Bug | #4225 | https://github.com/bridge5/amss-workbench/issues/4225 | Liaoxuan | QA: 1; QA: 4
12 | 康养1 | Bug | #4226 | https://github.com/bridge5/amss-workbench/issues/4226 | Liaoxuan | QA: 1; QA: 4
13 | Mixeduse 1 | Feature | #180 | https://github.com/bridge5/amss-api-issues/issues/180 | Shifeng | QA: 3; QA: 3
14 | Sales 1 & Sales 2 | Feature | #317 | https://github.com/bridge5/amss-api-issues/issues/317 | Heri and Fenghe | QA: 4; QA: 2; 开发管理: Need heri and fenghe
15 | Sales 1 & Sales 2 | Bug | #46 | https://github.com/bridge5/amss-api-issues/issues/46 | Heri | QA: 5; QA: 2
16 | Hotel 1 | Bug | #298 | https://github.com/bridge5/amss-api-issues/issues/298 | Shifeng | QA: 1; QA: 5
17 | Hotel 1 | Bug | #343 | https://github.com/bridge5/amss-api-issues/issues/343 | Shifeng | QA: 1; QA: 3
18 | Hotel 1 | Bug | #341 | https://github.com/bridge5/amss-api-issues/issues/341 | Shifeng | QA: 1; QA: 3
19 | Hotel 1 | Bug | #256 | https://github.com/bridge5/amss-api-issues/issues/256 | Shifeng | QA: 1; QA: 5
20 | Hotel 1 | Bug | #340 | https://github.com/bridge5/amss-api-issues/issues/340 | Shifeng | QA: 1; QA: 3
21 | Sales 1 | Bug | #351 | https://github.com/bridge5/amss-api-issues/issues/351 | Fenghe | QA: 3; QA: 4
22 | Retail 1 | Feature | #296 | https://github.com/bridge5/amss-api-issues/issues/296 | Yingcheng | bar: QA to QA
23 | Office 1 | Feature | #290 | https://github.com/bridge5/amss-api-issues/issues/290 | Yujie | bar: QA to QA
24 | Retail 1 | Bug | #237 | https://github.com/bridge5/amss-api-issues/issues/237 | Yingcheng | QA: 4; QA: 2
25 | Retail 1 | Bug | #265 | https://github.com/bridge5/amss-api-issues/issues/265 | Yingcheng | QA: 1; QA: 2
26 | Sales 2 | Bug | #62 | https://github.com/bridge5/amss-api-issues/issues/62 | Heri and Xiaozhou | bar: QA to QA
27 | Sales 2 | Bug | #49 | https://github.com/bridge5/amss-api-issues/issues/49 | Heri | bar: QA to QA
28 | Sales 2 | Bug | #70 | https://github.com/bridge5/amss-api-issues/issues/70 | Heri | QA: 4; QA: 2
29 | Office 1 | Feature | #190 | https://github.com/bridge5/amss-api-issues/issues/190 | Yujie | bar: QA to QA
30 | Sales 2 | Bug | #193 | https://github.com/bridge5/amss-api-issues/issues/193 | Heri | bar: QA to QA
31 | 康养1 | Bug | #357 | https://github.com/bridge5/amss-api-issues/issues/357 | Xiaozhou | QA: 3; QA: 4
32 | 康养1 | Bug | #333 | https://github.com/bridge5/amss-api-issues/issues/333 | Fenghe | QA: 2; QA: 4
33 | 康养1 | Bug | #346 | https://github.com/bridge5/amss-api-issues/issues/346 | Shifeng | QA: 1; QA: 3
34 | 康养1 | Bug | #361 | https://github.com/bridge5/amss-api-issues/issues/361 | Fenghe | QA: 3; QA: 5
35 | 康养1 | Bug | #363 | https://github.com/bridge5/amss-api-issues/issues/363 | Shifeng | QA: 2; QA: 5
36 | 康养1 | Bug | #364 | https://github.com/bridge5/amss-api-issues/issues/364 | Fenghe | QA: 4; QA: 5
37 | 康养1 | Bug | #335 | https://github.com/bridge5/amss-api-issues/issues/335 | Fenghe | QA: 1; QA: 4