## 修复记录
工程师 | Bill
月份 | 2020-11-16
| QA | QA | QA | QA |  | QA | QA | 开发管理 | 工程师 | 自动计算 | QA | 工程师 | 工程师 | 工程师 | 工程师 | 工程师
序号 | 产品 | 分类 | Ticket no. | Link | 工程师 | 严重程度 | 紧急程度 | 计划工作时长（天） | 开始时间 | 目标完成时间 | 实际完成时间 | 当前状态 | 原代码截图 | 问题原因 | 解决方案 | 其他功能影响评估（数据流，其他功能影响评估）
1 | Admin | Bug | #140 | https://github.com/bridge5/amss-api-issues/issues/140 | Bill | QA: 5; QA: 5
2 | Admin | Bug | #118 | https://github.com/bridge5/amss-api-issues/issues/118 | Bill | QA: 5; QA: 5
3 | Account | Bug | #139 | https://github.com/bridge5/amss-api-issues/issues/139 | Bill | QA: 1; QA: 3
4 | Admin | Bug | #112 | https://github.com/bridge5/amss-api-issues/issues/112 | Bill | QA: 5; QA: 2; QA: 2020-11-06
5 | Admin | Bug | #46 | https://github.com/bridge5/amss-api-issues/issues/46 | Bill | QA: 5; QA: 2
6 | UI | Bug | #3372 #3436 #3363 | https://github.com/bridge5/amss-workbench/issues/3372 https://github.com/bridge5/amss-workbench/issues/3436 https://github.com/bridge5/amss-workbench/issues/3363 | Bill | QA: 3; QA: 2
7 | Sales1 | Feature | #3722 | https://github.com/bridge5/amss-workbench/issues/3722 | Bill | QA: 3; QA: 2
8 | Sales1 | Feature | #900 | https://github.com/bridge5/amss-workbench/issues/900 | Bill | QA: 2; QA: 1
9 | Sales1 | Feature | #1311 | https://github.com/bridge5/amss-workbench/issues/1311 | Bill | QA: 2; QA: 2
10 | Sales1 | Feature | #2568 | https://github.com/bridge5/amss-workbench/issues/2568 | Bill | bar: QA to QA
11 | Sales1 | Feature | #1987 | https://github.com/bridge5/amss-workbench/issues/1987 | Bill | QA: 3; QA: 5
12 | Sales1 | Feature | #1900 | https://github.com/bridge5/amss-workbench/issues/1900 | Bill | QA: 1; QA: 3
13 | Sales2 | Bug | #3405 | https://github.com/bridge5/amss-workbench/issues/3405 | Bill | QA: 1; QA: 2
14 | Sales1 | Feature | #2589 | https://github.com/bridge5/amss-workbench/issues/2589 | Bill | QA: 5; QA: 1; 开发管理: need bill and liulv
15 | Office1 | Bug | #2248 | https://github.com/bridge5/amss-workbench/issues/2248 | Bill | QA: 3; QA: 2
16 | Retail1 | Bug | #543 | https://github.com/bridge5/amss-workbench/issues/543 | Bill | bar: QA to QA
17 | Sales 1 | Feature | #3722 | https://github.com/bridge5/amss-workbench/issues/3722 | Heri and Bill | QA: 3; QA: 2; 开发管理: need bill and heri