## 修复记录
工程师
月份 | 2020-11-01
| QA | QA | QA | QA |  | QA | QA | 开发管理 | 工程师 | 自动计算 | QA | 工程师 | 工程师 | 工程师 | 工程师 | 工程师
序号 | 产品 | 分类 | Ticket no. | Link | 工程师 | 严重程度 | 紧急程度 | 计划工作时长（天） | 开始时间 | 目标完成时间 | 实际完成时间 | 当前状态 | 原代码截图 | 问题原因 | 解决方案 | 其他功能影响评估（数据流，其他功能影响评估） | Comment
1 | Retail1 | Bug | #45 | https://github.com/bridge5/amss-api-issues/issues/45 | Fenghe | QA: 5; QA: 5
2 | Office1 | Bug | #102 | https://github.com/bridge5/amss-api-issues/issues/102 | Fenghe | QA: 5; QA: 5; QA: 2020-11-05
3 | Office1 | Bug | #249 | https://github.com/bridge5/amss-api-issues/issues/249 | Fenghe | QA: 5; QA: 5
4 | Hotel1 | Bug | #273 | https://github.com/bridge5/amss-api-issues/issues/273 | Fenghe | QA: 5; QA: 5 | This one QA have move to other dev
5 | Sales1 | Bug | #111 | https://github.com/bridge5/amss-api-issues/issues/111 | Fenghe | QA: 4; QA: 5; QA: 2020-11-16 | This one need 2 developer
6 | Sales1 | Bug | #276 | https://github.com/bridge5/amss-api-issues/issues/276 | Fenghe | QA: 3; QA: 5
7 | Office1 | Feature | #284 | https://github.com/bridge5/amss-api-issues/issues/284 | Fenghe | QA: 5; QA: 2
8 | Sales1 | Feature | #317 | https://github.com/bridge5/amss-api-issues/issues/317 | Fenghe & Heri | [11 empty] | This one need 2 developer
9 | 康养1 | Bug | #361 | https://github.com/bridge5/amss-api-issues/issues/361 | Fenghe | QA: 3; QA: 5
10 | 康养1 | Bug | #364 | https://github.com/bridge5/amss-api-issues/issues/364 | Fenghe | QA: 4; QA: 5
11 | 康养1 | Bug | #335 | https://github.com/bridge5/amss-api-issues/issues/335 | Fenghe | QA: 1; QA: 4
12 | 康养1 | Bug | #366 | https://github.com/bridge5/amss-api-issues/issues/366 | Fenghe | QA: 4; QA: 4