## 修复记录
工程师 | Heri
月份 | 2020-11-16
| QA | QA | QA | QA |  | QA | QA | 开发管理 | 工程师 | 自动计算 | QA | 工程师 | 工程师 | 工程师 | 工程师 | 工程师
序号 | 产品 | 分类 | Ticket no. | Link | 工程师 | 严重程度 | 紧急程度 | 计划工作时长（天） | 开始时间 | 目标完成时间 | 实际完成时间 | 当前状态 | 原代码截图 | 问题原因 | 解决方案 | 其他功能影响评估（数据流，其他功能影响评估） | Comment
1 | Sales1 | Bug | #87 | https://github.com/bridge5/amss-api-issues/issues/87 | Heri | QA: 4; QA: 4; QA: 2020-11-09
2 | Sales1 | Bug | #319 | https://github.com/bridge5/amss-api-issues/issues/319 | Heri | QA: 2; QA: 4; QA: 2020-11-13
3 | Sales1 | Bug | #317 | https://github.com/bridge5/amss-api-issues/issues/317 | Heri and Fenghe | QA: 4; QA: 2 | This one need 2 dev
4 | Sales 1 | Feature | #3722 | https://github.com/bridge5/amss-workbench/issues/3722 | Heri and Bill | QA: 3; QA: 2; 开发管理: need bill and heri
5 | Sales 1 & Sales 2 | Bug | #46 | https://github.com/bridge5/amss-api-issues/issues/46 | Heri | QA: 5; QA: 2
6 | Sales 2 | Bug | #62 | https://github.com/bridge5/amss-api-issues/issues/62 | Heri and Xiaozhou | bar: QA to QA
7 | Sales 2 | Bug | #49 | https://github.com/bridge5/amss-api-issues/issues/49 | Heri | bar: QA to QA
8 | Sales 2 | Bug | #70 | https://github.com/bridge5/amss-api-issues/issues/70 | Heri | QA: 4; QA: 2
9 | Sales 2 | Bug | #193 | https://github.com/bridge5/amss-api-issues/issues/193 | Heri | bar: QA to QA

## 截图1
https://github.com/bridge5/amss-api-issues/issues/317